Select any team name you prefer.
Please enter your name as it appears in Canvas.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
        Select "Completed Day 1" if finished on the first day, and
        similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product Backlog
Project Name	School Management And Reporting Tool (SMART)
Product Name:	Void PTR					Complete Fields in Green!!!
Team ID:	13					Product Backlog Burn Chart / Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required	Gerald Kimeu					GMK	1001869115

Sprint #	Remaining	Completed This Sprint				Comment
0	26				Total	Total number of features (in column H)
1	21	5			1	Total features left at the end of Sprint #1
2	15	6			2	Total features left at the end of Sprint #2
3	10	5			3	...and so on
4	6	4
5	2	4
6	-2	4

©2016-2021 by George F. Rice
This work is licensed under a Creative Commons Attribution 4.0 International License.						Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
						Additional features may be proposed by the student but must be approved by the Product Owner in writing
						Features
Feature ID	Priority	Required	Bonus	Est	Planned	Status	As a(n)…	I want to...	So that I can…	Notes
PERSON	1	1		13	1	Finished in Sprint 1	Administrator	Track people’s names and email addresses	Find and contact them	Need a Person base class with to_string / operator<< name and a full_info method
STUDENT	2	1		8	1	Finished in Sprint 1	Administrator	Track students by grade	Verify students’ progress	Need a Student derived class that includes the grade level (1-12)
PARENT	3	1		3	1	Finished in Sprint 1	Administrator	Track parents	Coordinate on student progress	Need a Parent derived class
RELATE	4	1		5	1	Finished in Sprint 1	Administrator	Associate each student with parents bidirectionally	Know which parents to contact	Mutual aggregate relationship
CLI	5	1	25	13	1	Finished in Sprint 1	Administrator	Basic command line user interface	Verify the system before moving to a GUI	This is cli.cpp for sprint 1 only (optional for bonus points)
WINDOW	6	2		13	2	Finished in Sprint 2	All	Use a windowed rather than command line interface	Use SMART more intuitively	Create a main window with a menu bar, data area, and status bar
D_STUDENT	7	2		8	2	Finished in Sprint 2	Administrator	Create students via dialogs	Conveniently enter the data	Series of dialogs, one per constructor parameter, is OK
DISPLAY	8	2		5	2	Finished in Sprint 2	Teacher	See all current data in the main window	Keep up with students	Display full_info for students and parents in a table in the data area
D_PARENT	9	2		5	2	Finished in Sprint 2	Administrator	Create parents via dialogs	Conveniently enter the data	Series of dialogs, one per constructor parameter, is OK
D_RELATE	10	2		8	2	Finished in Sprint 2	Administrator	Relate students to parents via dialogs	Conveniently enter the data	Dialog listing students and entering index, then same for parents
NEW	11	2		2	2	Finished in Sprint 2	Administrator	Clear all data	Start a new school	Simply clear all elements from the vectors
SAVE	12	3		13	3	Finished in Sprint 3	All	Write the data to persistent storage	Don’t have to re-enter data	See Lecture 15 for an object-oriented strategy to create the file format
LOAD	13	3		8	3	Finished in Sprint 3	All	Load data for a school from persistent storage	Don’t have to re-enter data	Select file via a file chooser dialog
SAVEAS	14	3		8	3	Finished in Sprint 3	Administrator	Save data to a different filename	Create backups or baselines for new schools	Select filename via a file chooser dialog
TOOLBAR	15	3		5	3	Finished in Sprint 3	All	Use the major features via a toolbar	Point and click	Suggest using the Nim game’s toolbar as a baseline
ABOUT	16	3		1	3	Finished in Sprint 3	Administrator	Display an About dialog with creator and version	Quickly determine which version is installed	Use Gtk::AboutDialog
AGG_IO	17	3	25	21			Administrator	Also save the aggregate data	Relationships are not lost	This is obviously critical in a real application
SUBJECT	18	4		5	4	Finished in Sprint 4	Administrator	Select from a list of subjects offered	Defined courses for the students to take	These can be hard-coded – you may select the courses you offer (minimum 5)
COURSE	19	4		13	4	Finished in Sprint 4	Administrator	Specify the courses to be offered to students	Give the students the needed knowledge	You may still use EntryDialog for these if you don’t have time for unified dialogs
SEMESTER	20	4		5	4	Finished in Sprint 4	Administrator	Specify the semester and year	Define when courses are offered	fall, spring and summer are sufficient here
SECTION	21	4		13	4	Finished in Sprint 4	Administrator	Define specific sections of each course	Students (and eventually teachers) unite
CBC	22	4		13	5	Finished in Sprint 5	Administrator	Use a single dialog for related parents and students	Enter data more efficiently	Derive a self-populating template from Gtk::ComboBoxText – see requirements
TEACHER	23	5		8	5	In Work	Teacher	Track the subject mastery and sections taught	Know who’s teaching what each semester	This is the third class derived from Person
GRADE	24	5		3	5	In Work	Student	Define the grading system	Quantify academic progress	This is another enum class, with the same supporting functions
TRANSCRIPT	25	5		8	5	In Work	Student	Link student to classes with a grade	Track schedule and balance assignments	This is a Transcript association class that references a Student and Section with a Grade attribute (X means in progress). Store in a Mainwin::transcripts vector.
ITERATORS	26	5		8	5	Finished in Sprint 5		TBD

						BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
UNIFIED			36	13	5	Finished in Sprint 5	All	Replace all remaining dialog sequences with unified dialogs each	Enter data more quickly	This covers the 6 main dialogs – 5 data types plus the association class (student to section). Each unified dialog earns 6 points.
EDIT			36	13			Administrator	Permit editing the 5 major data types – students, parents, teachers, courses, and sections	Correct errors and changing personal info	Prerequisite: UNIFIED for an editable dialog. The same dialog that created the data can be used to edit it – just set the current values as defaults. An additional 6 points per dialog is awarded for editing the data. Consider an Edit menu.
SCROLL			10	5			All	Make the main window’s data area scrollable	See large volumes of data	This is easier than it sounds. The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
STATUS++			15	8			All	Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack	Better track status of messages	Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages
MULTI			70	34			Administrator	Permit multiple schools to be open simultaneously	Support work at the district level or above	As shown at the end of the Sprint 1 requirements, move the data management to a School class, with methods for Mainwin to handle a school. Mainwin then stores a vector of pointers to the open Schools, with one “active” at any given time (usually selected by a Window menu, but tabs also work well). This is similar to how Microsoft Office handles multiple open documents.
PHOTO			40	21			Teacher	Include photos of students	Learn students names more quickly	The photos can be stored as JPEG files in the program directory (since we have no database), so store the filename as a Student attribute and use a Gtk::Image to display it.
GPA			15	8			Student	List all classes with grades and a cumulative GPA	Enable students and their parents to track academic progress	List all of the classes ever attended by a selected student, the grade earned for each. Calculate and present a cumulative GPA (average of 4 points for an A, 3 for B, 2 for C, 1 for D, and 0 for F – omit I and X grades).

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Mar 02		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 09		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	0
Day 1 Left	0	0
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0
			Note: Due to the late project start, the results of this sprint will be provided to you (although you may use your own solution if you prefer)
Task ID	Feature ID	Assigned To	Task	Status	Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Mar 09		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 23		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	8
Day 1 Left	7	1
Day 2 Left	6	1
Day 3 Left	5	1
Day 4 Left	3	2
Day 5 Left	1	2
Day 6 Left	0	1
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	WINDOW	GMK	Copy the base line code for windows	Completed Day 1	push to github after baseline is completed
2	WINDOW	GMK	Edit the mainwin to fit the current project	Completed Day 2
3	DISPLAY	GMK	Display The basic window with file, relate, relate	Completed Day 3
4	D_STUDENT	GMK	add information required to display the students	Completed Day 4
5	D_PARENT	GMK	add information required to display the parent	Completed Day 4
6	D_RELATE	GMK	add information required to display the relationship between student and parent	Completed Day 5	relate throws error when relating a student to 2 parents
7	DISPLAY	GMK	display all parent and student info	Completed Day 5
8	D_RELATE	GMK	Fix : relate throws error when relating a student to 2 parents	Completed Day 6
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Mar 23		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 30		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	5
Day 1 Left	5	0
Day 2 Left	4	1
Day 3 Left	3	1
Day 4 Left	1	2
Day 5 Left	0	1
Day 6 Left	0	0
Day 7 Left	0	0
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	SAVE	GMK	Write the data to persistent storage	Completed Day 4
2	SAVEAS	GMK	Save data to a different filename	Completed Day 4
3	TOOLBAR	GMK	Use the major features via a toolbar	Completed Day 3
4	ABOUT	GMK	Display an About dialog with creator and version	Completed Day 2
5	LOAD	GMK	Load data for a school from persistent storage	Completed Day 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Apr 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 13		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	27
Day 1 Left	27	0
Day 2 Left	27	0
Day 3 Left	27	0
Day 4 Left	27	0
Day 5 Left	23	4
Day 6 Left	11	12
Day 7 Left	4	7
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	SEMESTER	GMK	Write Semester enum	In Work
2	SEMESTER	GMK	Implement operator<<	In Work
3	SEMESTER	GMK	Implement load_semester	In Work
4
5	SUBJECT	GMK	Write Subject enum	Completed Day 5
6	SUBJECT	GMK	Implement operator<<	Completed Day 5
7	SUBJECT	GMK	Implement load_subject	Completed Day 5
8	SUBJECT	GMK	Write subjects_vector (for iteration)	Completed Day 5
9
10	COURSE	GMK	Write Course class	Completed Day 6
11	COURSE	GMK	Implement operator<<	Completed Day 6
12	COURSE	GMK	Implement Course::save	Completed Day 6
13	COURSE	GMK	Implement Course::Course(ist)	Completed Day 6
14
15	SECTION	GMK	Write Section class	Completed Day 6
16	SECTION	GMK	Implement operator<<	Completed Day 6
17	SECTION	GMK	Implement Section::save	Completed Day 6
18	SECTION	GMK	Implement Section::Course(ist)	Completed Day 6
19
20	WINDOW	GMK	Mainwin: Add Insert > Course and Section	Completed Day 6
21	WINDOW	GMK	Find new toolbar buttons and credit in Help > About	Completed Day 6
22	WINDOW	GMK	Mainwin: Add toolbar buttons for Course and Section	Completed Day 6
23
24	WINDOW	GMK	Mainwin: Add View > Students, Parents, Courses, Sections	Completed Day 7
25	WINDOW	GMK	Add View enum and View parameter to show_data	Completed Day 7
26	WINDOW	GMK	Add static current_view to show_data to remember view	Completed Day 7
27	WINDOW	GMK	Update show_data to show different data types	Completed Day 6
28
29	WINDOW	GMK	Write Mainwin::on_new_course_click using EntryDialog	Completed Day 7
30	WINDOW	GMK	Write Mainwin::on_new_section_click using EntryDialog	Completed Day 7
31
32	WINDOW	GMK	Mainwin: Update on_save_click to save courses and sections	Completed Day 7
33	WINDOW	GMK	Mainwin: Update on_open_click to load courses and sections	Completed Day 7
34	WINDOW	GMK	Mainwin: Add logic to load v0.1 files (pre-courses/sections)	In Work
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Apr 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 20		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	7
Day 1 Left	7	0
Day 2 Left	6	1
Day 3 Left	5	1
Day 4 Left	4	1
Day 5 Left	3	1
Day 6 Left	2	1
Day 7 Left	0	2
			ADD tasks below to complete each feature for THIS sprint
Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CBC	GMK	Use a single dialog for related parents and students	Completed Day 2
2	TRANSCRIPT	GMK	Track the subject mastery and sections taught	Completed Day 6
3	GRADE	GMK	Define the grading system	Completed Day 3
4	TRANSCRIPT	GMK	Link student to classes with a grade	Completed Day 7
5	TEACHER	GMK	Complete Teacher Class	Completed Day 5
6	ITERATORS	GMK	Create template with Iterators	Completed Day 4
7	SECTION	GMK	Add teacher and have it save and open with section	Completed Day 7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84